## Test Cases
Project Name |  | Vartex Bazar | TC Start Date | 21.12.2023 | TC Execution Start date | 25.12.23 | [6 empty] | TEST CASE SUMMARY
Module Name |  | Registration & Login | TC End Date | 22.12.2023 | TC Execution End Date | 25.12.23 |  |  |  |  | Pass |  | 39
Epic |  |  | Test Case Developed By | Md. Mazharul Islam | Browser () | No |  |  |  |  | Faill |  | 6
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance () | No |  |  |  |  | Not Executed |  | 0
Test Executed BY | [10 empty] | Out of Scope |  | 0
[11 empty] | Total |  | 45
#SL | Modules | Types of Testing | Features | Test Cases Description | Test Step Description | Test Data | Expected Result | Actual Result | Bug ScreenShot | Dev Coments | Final Status | Remarks
1 |  | Browsing Compatibility Testing |  | Checking by running the site in different browsers | Go to different browser> serach Vertex Bazar >Go to Website | Chrome, FireFox | Should run in different browsers | Found as per expectation |  |  | Passed
2 | User Management | UI Testing | Registration | Checking spelling or gramatical mistakes | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form. 3. Check the spelling and grammar of the website | N/A | No spelling or grametical mistakes | Found as per expectation |  |  | Passed
3 |  |  |  | Verifiying fonts, text color and styles | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Register button at the right corner 3. Check the font,text color , and styles | N/A | Should be as per requirement | Found as per expectation |  |  | Passed
4 |  |  |  | Veryfying mandatory red assterik field | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the register form 3. Check the assterik field | N/A | Red astarik should be present | Found as per expectation |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner and see register form 3. Check by clicking hovar the field | N/A | A text should appear over the field | Found as per expectation |  |  | Passed
6 |  |  |  | Checking alignment of the field | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the register form 3. Check the alignment of he field | N/A | Proper alignment of the field should be presnt | Found as per expectation |  |  | Passed
7 |  |  |  | Checking " eye" icon beside password field | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the register form 3. Check the eye icon beside the password | N/A | Eye icon should be present beside password field | Not found as per expectation | Eye icon defects |  | Failled
8 |  |  |  | Checking register button hover color | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Register button at the right corner 3. Check the button hover field | N/A | should be as per requirement | Found as per expectation |  |  | Passed
9 |  |  | Login | Checking spelling or gramatical mistakes | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. Check the gramatical mistakes | N/A | No spelling or grametical mistakes | Found as per expectation |  |  | Passed
10 |  |  |  | Verifiying fonts, text color and styles | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. Check the fonts, text color & styles | N/A | Should be as per requirment | Found as per requirement |  |  | Passed
11 |  |  |  | Veryfying mandatory red assterik field | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. Check the assterik field | N/A | Red astarik shuold be present | Found as per requirement |  |  | Passed
12 |  |  |  | Clicking by hovering over the field, | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. Check the hovering over the field | N/A | A text should appear over the field | Found as per requirement |  |  | Passed
13 |  |  |  | Checking " eye" icon beside password field | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. Check the eye icon beside password field. | N/A | Eye icon should be present beside password field | Not found as per requirement | Eye icon Defects |  | Failled
14 |  |  |  | Checking alignment of the field | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. Check the allignment of the field | N/A | Should be as per requirment | Found as per requirement |  |  | Passed
15 |  |  |  | Checkbox beside 'Remember Me' | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. Check the checkbox beside " remember me" | N/A | Should be as per requirment | Found as per requirement |  |  | Passed
16 |  |  |  | Checking 'Remember Me' checkbox is not enabled by default | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. Check the " remember me" checkbox not enable default | N/A | should not enabled by default | Found as per requirement |  |  | Passed
17 |  |  |  | Checking Login hover button | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. Check the login hover button | N/A | Should be as per requirment | Found as per requirement |  |  | Passed
18 |  | Functionality Testing | Registration | Keeping mandatory fields blank | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. Keep mandatory fields blank | N/A | Should be as per the requirement | Found Error: Please provide a valid email address, pasword, username |  |  | Passed
19 |  |  |  | Checking username is case insensetive | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. Check case sensetive using test data | SHAMErM shMamem | Should accept the provide input | Found as per requirement |  |  | Passed
20 |  |  |  | Inputing username with numbers | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the number | 123455 | Should not accept the provide input | Not Found as per expectation | Number Defects |  | Failed
21 |  |  |  | Inputing user name more than 32 character | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input username more tan 32 caracters | weetretretryhrthbgfnhgjyjuyjyjghnbvbvf | Should not accept the provide input | Not Found as per expectation | 32 characters |  | Failed
22 |  |  |  | Inputing username with special characters | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the username special characters | !@#$%^& | Should not accept the provide input | Found as per expectation | r |  | Passed
23 |  |  |  | inputing username with spaces | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the spaces |  | Should not accept the provide input | Found as per expectation |  |  | Passed
24 |  |  |  | Inputing space between username | Username input field > enter username> clicked Register | sham seem | Should not accept the provide input and display an error message | Not found as per requirement | Space defects |  | Failed
25 |  |  |  | Validating an username can only be used one time | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the user name | shameem | Should not allow user to register and display a pop message | Found as per expectation with an error message |  |  | Passed
26 |  |  |  | Checking Number email format | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the number email | 1234454@gmail.com | Should not allow user to register and display a pop message | Not found as per expectation | Number email |  | Failed
27 |  |  |  | Checking by inputing invalid email format | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the invalid email formate | lisakew507@com | Should not accept the provided input and display an error message | Found as per expectation with an error message |  |  | Passed
28 |  |  |  | Checking by inputing valid email format | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the valid email formate | sheem31.pr@gmail.com | Should be alow to register | Found as per requirement |  |  | Passed
29 |  |  |  | Validating an email can only be used one time | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the one time nvalid email | sheem31.pr@gmail.com | Should not accept the provided input and display an error message | Found as per expectation |  |  | Passed
30 |  |  |  | Inputing lower password | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the lower password | 1234567 | Should not accept the lower password and display showing at least 12 character long. use lowercase uppercase, number, symbols and not clicked on register button | Found as per requirement |  |  | Passed
31 |  |  |  | Checking strong password | 1.Go to the URL: https://vertexbazaar.com. 2. Click on Account button at the right corner and see register form 3. input the strong password | 8f6Ti3h5gDt#m5Y | should be accepted the the strong password and registered | Found as per requirement |  |  | Passed
32 |  |  | Log In | Keeping email and password field blank | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. keeping field blank | N/A | Should not allow user to login and display error message | Found as per expectation |  |  | Passed
33 |  |  |  | Checking if the data in password is masked | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. check data masked | 8f6Ti3h5gDt#m5Y | Should be masked | Found as per expectation |  |  | Passed
34 |  |  |  | Checking login wrong credentials in username/email and password field | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. input wrong credentials | sham seem / lisakew507@com | Should not allow user to login and display error massage | Found as per expectation |  |  | Passed
35 | [5 empty] | Pass: 1234567 |  |  |  |  | Passed
36 |  |  |  | Checking Login valid credentials is username/email and password field | 1.Go to the URL: https://vertexbazaar.com. 2. Click on account button at the right corner & see the login form 3. input user credentials click login | sheempi/sheem31.pr@gmail.com | Should not allow user to login | Found as per expectation |  |  | Passed
37 | [5 empty] | pass: 8f6Ti3h5gDt#m5Y |  |  |  |  | Passed
38 |  |  |  | Verifying ‘Forgot Password’ functionality | 1.Go to the URL: https://vertexbazaar.com 2. Click on account button at the right corner & see the login form 3. Click on Forgot password 4. Check email | N/A | Should sent an email for recovering password | Found as per expectation |  |  | Passed
39 |  |  |  | Checking by selecting ‘Forgot Password’ multiple times | [6 empty] | Passed
40 |  |  |  | Verifying change the password link is sent to valid email address | 1.Go to the URL: https://vertexbazaar.com 2. Click on account button at the right corner & see the login form 3. Click on Forgot password 4. Check registered email 5. click reset the password | mazhar31.cs@gmail.com | Should be sent to valid email address | Found as per expectation |  |  | Passed
41 |  |  |  | Verifying the functionality of 'Set a New Password' | 1.Go to the URL: https://vertexbazaar.com 2. Click on account button at the right corner & see the login form 3. Click on Forgot password 4. Check registered email 5. click reset the password 6. type new password and retype new password 7. save password | pass:!@#$%^&qwertyasdfgz | Showing password change succesfully | Found as per expectation |  |  | Passed
42 |  |  |  | Verifying login with the newly changed password | 1.Go to the URL: https://vertexbazaar.com 2. Click on account button at the right corner & see the login form 3.click login | email: mazhar31.cs@gmail.com pass: !@#$%^&qwertyasdfgz | showing Login Succesfully | Found as per expectation |  |  | Passed
43 |  | Usability Testing | Registration & Login | Checking copy paste functionality in every field | 1.Go to the URL: https://vertexbazaar.com 2. Click on account button at the right corner 3 Click every field and paste every field | shameem345 | Should copy and paste text from fields | Functioning successfully |  |  | Passed
44 |  |  |  | Checking keyboard tab button functionality | 1.Go to the URL: https://vertexbazaar.com 2. Click on account button at the right corner 3 Click tab button to another field switch | Enter tab in every field | Should switch to another field and highlight text | Functioning successfully |  |  | Passed
45 |  |  |  | Checking keyboard enter button functionality | 1.Go to the URL: https://vertexbazaar.com 2. Click on account button at the right corner 3 Click input enter in every field | Input enter tab in every field | Should switch to another field | Functioning successfully |  |  | Passed
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85

## Summary Report
Test Case Summary Report | [5 empty] | Total No. | Status | Result :
Project Name | Vertex Bazaar |  |  |  |  | 39 | PASS
Module Name | Registration & Login |  |  |  |  | 6 | FAIL
Test Case Version | [5 empty] | 0 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Written By | Md. Mazharul Islam |  |  |  |  | 0 | Out of Scope
Executed By | Md. Mazharul Islam
Reviewed By | Ehsanul Alam Sabbir
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 39 | 6 | 0 | 0 | 45
Grand Total | 39 | 6 | 0 | 0 | 45
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (45/45)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/45)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (39/45)*100 =86.66
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (6/45)*100 = 13.33
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/62)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A